## Slide 1: WB DTDS Websphere Migration
2014

## Slide 2: Tech Mahindra ADMS Service Offerings
Application Development
Solution Architecture Definition
Enterprise Application Integration
Development Methodologies and Tools
SOA Services
Application Migration
Solution Architecture Assessment
Prominent Java Frameworks - Spring, Hibernate, JSF, GWT, smartGWT, Hibernate, Struts
JEE 6 Platform - CDI, EJB, JSF, JMS, JPA, JAX-WS, JAX-RS, JAAS, Java GS
Using Grails, Rails, PHP
Layered Architecture, Modularization, Security, Error Handling, Audit Logging
Capacity Planning, Estimation Modeling
Develop Architecture Blueprint
Architecture Review & Recommendation
Develop Enterprise Integration Methodology
Focus on Quality of Service parameters: Scalability, Performance, Interoperability, Usability
Define System Integration Components
Focus on Standards, Security, Performance and Interoperability
Waterfall and Agile Development Methodologies
Agile and Application Life Cycle Management Tools
Continuous Integration Tools – Jenkins, Ant, Hudson, Sonar, Maven
Define SOA based Solution Architecture
Service Identifiation, Design and Development
SOA Governance
Legacy Migration from Mainframe, ColdFusion, Oracle Forms to Java
Application modernization using latest Java Frameworks
Performance Engineering
Develop Performance Analysis and Tuning Framework
Tools for Load Testing and Performance Analysis
Design Reviews for Performance Improvement

## Slide 3: ADMS Java & Open source Competency Snapshot
Delivery Experience
Alliances
Technology Expertise
Practice Highlights
9500+ Java & J2EE Developers
600+ Experts in the Service Offering Team
400+ Certified Specialists for Analysis & Design
400+ Technical Architect Pool International Certifications
International Certifications
4000+ Sun Certified Associates with certifications like SCJP, SCJA, SCJD, SCWCD
600+ IBM Certified Associates on Rational (RSA, Requisite Pro etc.) & Websphere Suite of Products
Associates also certified on frameworks like Hibernate & Struts
275+ Projects currently running
  150+ Fixed Bid Projects
30% Project Managers are PMP Certified
Strong delivery team providing rich Project expertise
Tight Integration between Technology Experts & Project Teams (SO Team & Delivery Team)
Standardized Development Frameworks (GWT, JSF, SPRING, STRUTS, Jtrac, Wicket)
Agile development practices (XP, Scrum, FDD)
RUP & Waterfall Delivery Methodology
Presentation : PHP, Pearl, Python, Ajax, Spring, Struts, Wicket, Seam, JSF
Business Process : Weblogic , WebSphere Process Server, jBPM
Intalio Process Server, EJB
Service Layer : Mule, Websphere ESB, Aqualogic ESB, JBoss ESB, Tibco ESB
& SOA
Application Server: JBoss, Weblogic, Java Application Server, WAS CE,
Websphere, Tomcat
Application Blocks : JBOSS (Cache, Rules), IBM Portal, Liferay
& Portals
Data Layer : Hibernate, TopLink, MySQL, Oracle, DB2, DB Ingress
Content Management : Confluence, Drupal, Joomla, Alfresco
Identity Management : Netigrity, Source ID, Tivoli IAM, Sun IAM
User Authentication : Java Authentication and Authorization Service
Development Tools : Eclipse, JBoss Developer Studio, IBM RAD
Processes : RAD, Agile, Waterfall

## Slide 4: Tech Mahindra’s Server Migration Framework
6 Step Migration Process – Platform and Technology Neutral
1
Architecture
Assessment
2
Solution
Modeling
3
Execution
4
Testing
5
Post Migration Support
Analyze AS-IS /
TO-BE Architectural Blueprints
Apps Migration Analysis and planning
Infra Migration Planning
Recommend target Infra setup and application configuration
Service Modeling
Infra Design and Network Topology
Provision and Configure Infrastructure
Configure Application/DB on new Environment
Rebuild Source Code, Databases on new environment
Develop Test Cases / Scenarios
L1, L2, L3 Infra and Apps Support
0
Pre-Migration
Application Portfolio Analysis
Wave and Micro Wave Analysis
Catalog Definitions
Capacity Planning
Migration Methodology
Create Detail design of target application
Setup Development Environment
Release management and Deployment
Create Test Cases Suite
Finalize Test Plan
Finalize on migration Team
Design and Setup all The Environments
Application Testing on Cloud:
1. Performance
2. Security
3. Availability
4. DR
5. Functional
6. Scalability
Discover and assess existing Infra setup with assessment tools
Analyze, Understand and finalize on target Deployment model
Creation of various infra components like VMs, in target environment
Setup monitoring tools
Setup Support Team
Trouble ticketing and issue resolution

## Slide 5
Server Migration Methodology
Capacity planning
New Hardware Introduction
Old Hardware Footprint Reduction
Leverage Sizing calculator based on Source and Target CPU speed
Confirm with Vendors on the sizing
Perform scaled down performance analysis
Include new Hardware iteratively as part of the cluster horizontally
Share load progressively starting with non-peak hours
Increase the load to peak hrs
Share the load equally between old and new hardware
Reduce the Load on the old Hardware progressively
Monitor the Parallel Run results
Stop the traffic to old hardware and keep on hot standby
Monitoring the performance of the new Hardware
Old Hardware Removal
Monitor the results of the new hardware throughput
With favourable results, old hardware can be decommissioned and declare GO-LIVE
Pre-production Environment
Environment Setup
Application deployment
Functional and non-functional testing
Production environment
Platform & Application set up
Repeat the logic for hardware management
Assess the test results and declare GO-LIVE

## Slide 6: Application Migration Stratergy
Application Inventory & Dependency Analysis
Application and Infrastructure Inventory
Identify Code Dependencies
Migration & Unit Testing
Infrastructure Setup
System & Performance Testing
Application Deployment
Group Applications by Target Platform, Tech Stack and Complexity
High-level Migration Planning (PoC and Application Group)
Deployment & Warranty
Application Grouping & Planning
Code Retrofitting
Performance and Security Testing
Pre-Conversion Testing
Procure / Prepare Regression Test Cases
Capture Test Results
Regression Testing
Compare Pre & Post Test Results
Migration Issues Analysis
Unit & System Testing of Changes
UAT
Warranty Support
Unit Testing
Identify
3rd Party Components
used
Code Changes
Basic Performance Testing
Regression Testing
Production Deployment
System/
Integration Testing
Baseline Code
Infrastructure Planning
MSAT Scope
SBI on Pre-Prod

## Slide 7: Migration Approach
Initiate migration assessment
Due diligence of the existing environment
Application Portfolio analysis for suitability
Due diligence of the To-Be environment
Documentation of the environment differences
Due diligence of the Application based on environment differences
Perform environment changes in the To-Be environment
Perform application changes
Create and Update Test Cases
Create Test Plans
Infrastructure Testing
Functional Testing
Performance & Load Testing
Failover Testing
Intrusion Detection
Penetration Testing
High Availability Testing
Disaster Recovery Testing
Security Testing
Functional Testing
Accessibility Testing
Front End Validations
Web Services Testing
Bi-lingual Testing
Multi-country Testing
Regression Testing
Vulnerability Testing
Load Testing
Stress Testing
Peak (2x) load Testing
Durability Testing
Migration
Approach
Migration
Testing

## Slide 8: Migration Planning
Identify current hardware and operating system specification
Operating system and version
Collect current application software specifications
Application server and version
Perform Application Reviews
Application review to identify any code or configuration incompatibilities
Identify code or configuration modifications
Number and type of processors
Memory capacity
Size and type of physical disks/storage
Additional application server components such as portal, ESB, or business process mapping tools
Third party, vendor-specific, and open source components or libraries
JVM and JRE versions
Integrated applications
Clustering configurations
Review Build & Deployment
Identify processes having direct coupling to the current application server environment
Identify modifications in monitoring and administration procedures and tools to integrate with Enterprise Application Platform

## Slide 9: Migration Execution
Standard Migration Tasks
Configuration changes
Additional Migration Factors
Non-standard Object-Relational Mapping (ORM) framework
Enhancements
Upgrade the build process for the new environment
JMS Queues, Topics, and Persistence
JNDI port configuration
Deployment descriptor changes
Logging
JDBC pooling and configurations
Library upgrades
Build process and/or directory structures changes
Deployment changes
Monitoring/instrumentation changes
Proprietary component of the application server needs to be converted
Clustering and Caching mechanisms, such as session replication, handling of SFSB, and the use of proprietary caching APIs
Connections to third party systems (e.g., integration adapters to SAP, Siebel, PeopleSoft, etc)
Incorporate leading open source frameworks
Evaluate the overall application architecture for performance, maintainability, scalability and usability improvements.
Introduce Clustering into the application for High Availability
Migration Testing
Functional Testing
Testing changes
Performance and Security Testing

## Slide 10: TechM Migration Methodology
Phase | Tasks | Deliverables | Typical Duration
Phase I: Analyze Server architecture & deployment model | - Collect inventory of existing servers, network infrastructure and applications - Establish baseline of existing functionality and load capacity | Server and Application Inventory with details of purpose, usage, configuration and hardware | 2-4 weeks
Phase II: Application migration assessment | - Assess individual applications for migration - Examine dependency on standards and proprietary libraries - Assess adherence to standard specifications and impact | List of suitable applications with migration priority; Prioritized list of applications suitable for migration; List Proprietary libraries used by applications; Migration specification | 2-12 weeks (depends on number and complexity os apps)
Phase III: Effort and risk assessment | - Assess application functionality to be deployed on servers - Estimate migration effort for each application - Identify risks and prepare mitigation plan | Server-wise service configuration list; Definition of clusters and cluster configuration; Estimated effort for each migrating; Identification of risks for each application | 4-6 weeks
Phase IV: Server and application migration plan | - Define the roadmap for migrating servers and applications - Define open source alternatives to propreitery libraries and services | Server migration plan with services and configuration to be migrated for each server/cluster; Application migration plan detailing library changes and code changes required to migrate each application | 5-8 weeks
Phase V: Migration implementation | - Execute migration paln | Successful migration | TBD

## Slide 11: Migration Methodology PHASE I: Analyze Server Architecture and Deployment Model
Infrastructure Analysis
  Datacenters: Number of Datacenters, Datacenter interconnectivity, Servers, Hardware etc.
  Failover strategy
  Software: Load balancers, static web server, dynamic web server, GUI, etc.
  Ancillary services: Messaging, portal, AOP, injection, caching, etc.
  Development environment: IDEs, Development methodology, Build Tools, etc.
  Applications: Applications running on servers, business criticality

## Slide 12: Migration Methodology PHASE II: Application Migration Assessment
Application Analysis
  Deciding migration targets for used Technologies
Component | Features
Monitoring and management | Remote control and configuration, threshold notification, etc.
Web server | Servlet container, state replication
Messaging | Participate in transactions, persistence of messages, bridges outside cluster, JMS specifications
Caching | Transactional, distributed, object graph support
Clustering and replication | Layered replication, transaction-safe replication, fine-grained
Persistence | Supported databases, support for flat file systems, hybrid data stores, transaction support and database feature support
Security | Authentication, authorization single sign-on JAAS/JACC support, certificate support
Aspect-oriented programming | Cross-cutting concerns
Injection | Standard injection support
Presentation layer: JSP, JSF, Facelets, tag libraries | Compatibility and support for presentation standards
Transaction manager | Reliable transactional behavior, distributed support for latest technology

## Slide 13: Migration Methodology PHASE III: Effort and Risk Assessment
Technical Analysis
  Scope
  Number of servers, datacenters, and applications to be migrated
  Technology gap analysis
  Features that do not map to open source alternatives
  Conflicting configuration requirements
  Adherence to specifications
  Use of proprietary IDEs that embed proprietary libraries
  Library selection
Organizational Analysis
  Training and knowledge gaps
    Skill availability
    Adaptability for tools and technology changes
  Workload factors
    Current workload and additional bandwidth for training and migration
    Hardware availability for deployment, testing and production
  Budget
    CAPEX versus OPEX
    TCO versus ROI

## Slide 14: Migration Methodology PHASE IV: Server and Application Migration Plan
Define SOP (Standard Operating Environment) for Migration
  Define core operating system and middleware components including:
    Base operating system
    JEE container
    Custom configurations
    Standard applications used
    Software updates
    Service packs
Create Deployment Environment based on SOE
  Tested Hardware
  Tested Software
  Server Configurations by Application
  Server and Application Mapping
Plan Training Schedule
Cost estimation
  Staging Hardware costs for testing servers and configurations
  Customization Costs- Extensions and new development
  Group applications for cost estimation by configuration and source code changes
  Training costs
  Savings from reduced software costs
  Savings from redeployed hardware

## Slide 15: Migration Methodology PHASE V: Migration Implementation
Identify Projects to support Migration Plan
Develop detailed Project Plans
Identify major Project Milestones
Resource availability

## Slide 16: Parallel Operations
Old System – Production
New System – Pilot Deployment
Common Database
Compare results for Six weeks
Old System – Sun Set
New System – Full Scale Deployment
If Satisfactory Results
Yes
Yes
Continue Parallel Run
No
All System Users
Selected System Users & Admins
Cluster on Old Environment
Cluster on New Environment

## Slide 17
Data base migration approach

## Slide 18: Handling Typical Concerns and Issues
Business & IT Stakeholders
Moving away from a stable Application environment
Impact to Users and Customers
Business and Technology Benefits
Cost and Schedule
Resource skills and Training
Resource bandwidth to handle migration effort
Well-defined Migration Strategy
Develop Business Case
Proven Estimation Methodology and Tools
TechM IBM CoE
& Training Programs
TechM Migration Methodology,
Pre & Post Migration Testing
TechM Program Management and Outsourcing experience

## Slide 19: TechM Differentiators
Dedicated Java and Open source Competency
Strong Java and Open source skill base
Proven Migration Methodology
  Reusable knowledge repository with migration scenarios and solutions
  Iterative by an application or group of applications
  Adaptive model of accumulating solutions for migration issues typical to the current application environment
  Processes to promote reusability
  Repeatable processes
  Proven solutions resulting in reduced migration risk
  Effective usage of tools for automation
Value Realization
  Reducing the overall migration effort
  Saving Time
  Preventing errors
  Environment conducive for scaling resource skills

## Slide 20: Thank you
Visit us at www.techmahindra.com